## SIT Summary
SYSTEM INTEGRATION TESTING (SIT) REPORT
Project Name | Aramex Customs Charges Management (CCM) - MVP Release
Release / Build | Build 1.0 / MVP June 2026 Release
SIT Cycle | SIT Cycle 1
Test Environment | Stage (https://stage-cc.aramex.com/login)
Test Start Date | 2026-09-01
Test End Date | 2026-09-15
QA Manager | Aditi Singh (QA Lead)
Client / Business | Aramex / InfoAXS Modernization Team
Overall Status | Conditional Pass
SIT Execution Summary
Total Test Cases | 0
Executed | 0
Passed | 1038
Failed | 892
Blocked | 798
Not Executed | 68
Pass % | 26
Defects Raised | 146
Open Defects | 89.5%
Critical / High Open | 42
Key Observations / Risks
SIT Sign-off
QA | Name: | Date: | Status:
Development | Name: | Date: | Status:
Business / BA | Name: | Date: | Status:
Client | Name: | Date: | Status:

## Test Execution
TC ID | Module / Feature | Scenario | Test Case Description | Priority | Tester | Execution Date | Status | Defect ID | Defect Severity | Comments
SIT-001 | Login | Valid Login | Verify user can login with valid credentials | High |  |  | Not Executed
SIT-002 | Order | Create Order | Verify order creation and downstream integration | Critical |  |  | Not Executed

## Defect Summary
Defect ID | Module | Summary | Severity | Priority | Status | Raised Date | Assigned To | Target Fix Date | Retest Status | Closure Date | Comments

## Integration Coverage
Interface / Integration | Source System | Target System | Business Flow | Scenario | Expected Result | Actual Result | Status | Defect ID | Comments

## Daily Execution
Date | Tester | Planned TC | Executed TC | Passed | Failed | Blocked | Defects Raised | Critical/High Defects | Remarks
|  | 50 | 48 | 47 | 1 | 0 | 1 | 0
|  | 80 | 78 | 72 | 4 | 2 | 3 | 0
|  | 100 | 95 | 88 | 5 | 2 | 4 | 1
|  | 90 | 88 | 82 | 4 | 2 | 2 | 0
|  | 80 | 80 | 78 | 2 | 0 | 2 | 0
|  | 120 | 115 | 98 | 12 | 5 | 8 | 2
|  | 100 | 98 | 90 | 6 | 2 | 4 | 0
|  | 80 | 75 | 68 | 5 | 2 | 3 | 1
|  | 70 | 68 | 58 | 8 | 2 | 5 | 2
|  | 40 | 38 | 36 | 1 | 1 | 1 | 0
|  | 60 | 58 | 54 | 2 | 2 | 2 | 0
|  | 50 | 45 | 42 | 2 | 1 | 1 | 0

## Environment & Data
Item | Details | Version / Build | Owner | Status | Remarks
Application / Build | CCM Web Application v1.0 (MVP) | Build 1.0 | Aramex DevOps | Active | Stage environment validated
SIT Environment URL | https://stage-cc.aramex.com/login | Stage | QA Team | Active | Microsoft Entra ID SSO; Chrome 147+ / Edge 147+
Database | PostgreSQL (CCI Database) | Stage DB | DBA Team | Active | Shipment and charge table validation performed
Test Data | Test Data Sets (CSV/Excel fixtures) | CCIPH ticket-based | QA Team | Available | 101 data files; rate sheets, AWB uploads, B2B templates configured
API / Interface | REST APIs (Charge Creation, Manual Override, Exchange Rate) | Stage API endpoints | Dev Team | Active | API validation integrated in automation framework
External Dependency | InfoAXS (Exchange Rates, Shipment Messages) | External | Integration Team | Partial | Exchange rates active; shipment status updates deferred to next release